## Sponsor Inputs
# | High level ideas / Features
1 | Create Account
2 | View Restaurants
3 | Search Restaurants
4 | View Menu
5 | Add to Cart
6 | Purchase
7 | Restaurant views order
8 | Restaurant marks order as delivered
Notes:
1 | The above points were listed as draft ideas by the project sponsor.
2 | The project sponsor mentioned that he wants to compete against Talabat.
3 | As a sponsor, I am planning to compete against Talabat.
4 | This is a view only file, you can make a copy then edit in the copy.
5 | You can find a tab named Product Backlog Template, please feel free to use it when creating your product backlog.

## Product Backlog Template
# | Epic | User Story | Priority | Ready to be planned | Planned Sprint | Status
1 | Create Account | As a user, I want to create an account so that I can use the application | 1 |  | 1
2 |  | As a user, I want to log in so that I can place an order | 1 |  | 1
3 | View Restaurants | As a user, I want to browse the availible resturants so that I can choose from them | 1 |  | 1
4 |  | As a user, I want to view promo codes so that I can use them | 2 |  | 2
5 | View Menu | As a user, I want to view restaurants menus so that I can choose what I want | 1 |  | 1
6 | Search Restaurants | As a user, I want to search restaurants so that I can find specific one | 2 |  | 2
7 |  | As a user, I want to search restaurants by category so that It would easier for me | 2 |  | 2
8 | Purchase | As a user, I want to check my cart so that I can modify my order or to confirm it | 1 |  | 1
9 | Add to Cart | As a user, I want to place an order to get delivered | 1 |  | 1
10 |  | As a user, I want to checkout so that I can choose wether to pay in cash or card | 2 |  | 2
11 |  | As a user, I want to check my order so that I can track my order status | 2 |  | 2
12 | Restaurant views order | As a restaurant admin, I want to add new choices to my menu so that I can satisfy customer | 1 |  | 1
13 |  | As a restaurant admin, I want to specify each dish price so that it would be obvious to the customer | 1 |  | 1
14 |  | As a restaurant admin, I want to view orders from my restaurant so that I can start working on them | 1 |  | 1
15 | Restaurant marks order as delivered | As a restaurant admin, I want to mark the orders as delivered or not yet so that I can manage the left easily | 2 |  | 2